NAIC 2026 · Academia & Research · PS3 Sectoral Fine-Tuning

# Ilera-ATLAS: Data Sources, Free Stack and Execution Plan

Prepared 1 October 2026. Deadline: Monday 12 October 2026, 11:59 PM WAT. Every link in this document was checked on 1 October 2026.

# 1. What we are building (one paragraph)

Ilera-ATLAS is N-ATLaS fine-tuned (QLoRA) to answer primary-healthcare questions the way Nigeria's 2024 National Standing Orders for community health workers say they should be answered. Questions come in English, Hausa or Yoruba. Each answer starts with a clear action (treat at the PHC, refer, or urgent referral) and cites the Standing Orders section it came from. We prove it is better than base N-ATLaS on a frozen benchmark of 600+ items (Ilera-Bench) and serve it through a documented API plus a small demo page. Total cost: ₦0, using free GPU and hosting tiers.

| Deliverable | What it is | Where it lives |
| --- | --- | --- |
| Ilera-QA | 3,000 to 5,000 training pairs (English, Hausa, Yoruba) | Hugging Face dataset (private until submission) |
| Ilera-Bench | 600+ frozen, human-checked test items, plus an external AfriMed-QA test | Hugging Face dataset + eval script in GitHub |
| Ilera-ATLAS model | LoRA adapter, merged weights, GGUF Q4 build | Hugging Face model repo with model card |
| Ilera API | OpenAI-compatible endpoint + safety layer | Modal (GPU, free credits) + Hugging Face Space (CPU fallback) |
| Demo page | Gradio chat page for testers and the video | Hugging Face Space |
| Evidence pack | Results tables, tester logs, video, docs | GitHub repo + submission form |

# 2. Data: where to get it

Use official Nigerian clinical guidance as the source of truth, open datasets only for testing and general-language balance. Keep a SOURCES.md file listing every document, its link, and its licence. Judges and the model card both need it.

## 2.1 Core source: National Standing Orders (revised 2024)

Published by the Community Health Practitioners Registration Board of Nigeria (CHPRBN) with the Federal Ministry of Health and NPHCDA, unveiled 5 September 2024. Three levels exist; use all three because they define what each cadre may treat versus must refer.

| Document | Direct PDF (text version) |
| --- | --- |
| CHEW Standing Orders (main source) | CHEW-NATIONAL-STANDING-ORDERS-Section-1-7.pdf |
| JCHEW Standing Orders | JCHEW-Text-only-1-7-Sections.pdf |
| CHO Standing Orders | CHO-NATIONAL-STANDING-ORDERS-Section-1-8.pdf |
| CHEW illustrated version (good for case vignettes) | CHEW-Illustrated.pdf |
| Official landing pages | CHPRBN Standing Orders · PHC Workforce Hub |

## 2.2 Supporting clinical guidance

| Source | Use it for | Link |
| --- | --- | --- |
| WHO IMCI Chart Booklet (2014) | Childhood illness: danger signs, fast breathing, diarrhoea, malnutrition | who.int IMCI chart booklet) |
| National Malaria Elimination Programme (NMEP) | Nigerian malaria treatment guidelines | nmcp.gov.ng/publications |
| NCDC guidelines | Cholera, Lassa fever, other outbreak protocols relevant to PHC | ncdc.gov.ng/diseases/guidelines |

## 2.3 Open datasets

| Dataset | Licence | Use it for | Link |
| --- | --- | --- | --- |
| AfriMed-QA v2 (15,275 African medical Q&A, many Nigerian contributors) | CC-BY-SA-4.0, gated (auto-approve) | External test only. Pick a primary-care subset as a second benchmark. Do not mix into training, so the score stays honest. | HF: intronhealth/afrimedqa_v2 · GitHub |
| Aya Dataset (human-written instructions incl. Hausa, Yoruba, Igbo) | Apache-2.0 | Add about 10% general-language examples so the model does not forget how to chat normally | HF: CohereLabs/aya_dataset |
| MedQuAD (English consumer health Q&A) | Check card (original is CC BY 4.0) | Optional English padding only, if you are short of data | HF: MedQuad |

## 2.4 Data you create yourselves (the most valuable part)

- Draft Q&A from the Standing Orders: N-ATLaS reads one section at a time and drafts questions and structured answers; team members correct them in a Google Sheet.

- Case vignettes: short stories like "A 2-year-old has had fever for 3 days and breathes fast". These test reasoning, not memory.

- Referral cases: situations that are outside a CHEW's scope. The correct answer is "refer", and the model must learn to say so.

- Translations: N-ATLaS translates to Hausa and Yoruba; a native speaker fixes every benchmark item and a sample of training items.

- Red-flag list: 30 to 50 danger signs (convulsions, heavy bleeding in pregnancy, newborn not feeding, unconscious, etc.) in English, Hausa and Yoruba, approved by your clinical reviewer.

# 3. Free way to run the whole thing

| Stage | Free option (primary) | Free backup | Notes |
| --- | --- | --- | --- |
| PDF extraction, data cleaning | Your laptop or Kaggle CPU with PyMuPDF | Google Colab (free) | PyMuPDF docs |
| Draft generation and translation with N-ATLaS | Kaggle GPU notebook, N-ATLaS in 4-bit | Colab free T4 | About 30 GPU hours/week per Kaggle account (check your quota). Phone-verify the account to enable GPU and internet. |
| QLoRA training | Kaggle T4 + Unsloth | Second team member's Kaggle account; Colab | Start from the Unsloth Kaggle Llama-3.1-8B notebook and swap the model ID to NCAIR1/N-ATLaS. |
| Evaluation (base vs fine-tuned) | Kaggle T4 | Colab | Run both models on the same 600 items with the same settings. |
| Merge + GGUF export | Unsloth save_pretrained_gguf on Kaggle | llama.cpp converter | Unsloth GGUF guide |
| GPU API (what judges call) | Modal: Starter plan, $30/month free credits, scales to zero | Kaggle notebook + Cloudflare tunnel for live test sessions | Follow the Modal vLLM example. Set a spending limit of $0 above credits. |
| Always-on fallback API + demo page | Hugging Face Space, CPU Basic (2 vCPU, 16 GB RAM, free) running the Q4 GGUF with llama-cpp-python | - | Slow (a few tokens per second) and costs nothing. Free Spaces sleep after about 48 hours without visits and wake on the next request, so open it daily during judging. Fine for short answers and for judges who just want to see it work. |
| Code + docs | GitHub (public repo) | - | - |
| Model + datasets hosting | Hugging Face Hub (free) | - | Keep repos private until submission day. |
| Annotation | Google Sheets with a fixed column layout | Label Studio (free, self-hosted) | - |

## Why this fits on a free T4 (16 GB)

- N-ATLaS is a Llama-3 8B model. Loaded in 4-bit it uses about 6 GB, leaving room for LoRA training with sequence length 1,024 to 2,048.

- T4 has no bf16 support: use fp16 (Unsloth picks this automatically).

- Expected training time: about 1.5 to 3 hours for 4,000 examples x 2 epochs. Three team accounts give about 90 GPU hours a week, enough for 3 to 4 training runs plus evaluation.

- N-ATLaS is gated: every account that downloads it must accept the conditions on Hugging Face, then store an HF token as a Kaggle Secret (never paste it in the notebook).

## Optional spend if things get tight (still cheap)

- Colab Pro (about $10) for an L4/A100 if Kaggle quota runs out.

- Hugging Face PRO ($9/month) unlocks ZeroGPU Spaces for a fast free-to-use demo. Not required.

# 4. System design

## 4.1 Answer format (makes scoring automatic)

Every training answer follows the same short structure. This lets us score the action automatically, and it makes answers safer and easier for a CHEW to read.

ACTION: Treat at PHC | Refer | URGENT REFERRAL

WHAT TO DO:

1. ...

2. ...

DANGER SIGNS TO WATCH: ...

SOURCE: CHEW Standing Orders, Section 4.2 (Pneumonia in children)

Hausa and Yoruba answers use the same labels translated, plus the English label in brackets so the parser always works, for example MATAKI (ACTION): Tura zuwa asibiti (Refer).

## 4.2 Request flow

User question (en / ha / yo)

-> Safety layer: red-flag check (keyword list in 3 languages)

hit  -> force "URGENT REFERRAL" header + model explanation

-> Ilera-ATLAS (N-ATLaS + LoRA) generates structured answer

-> Post-check: answer has ACTION + SOURCE lines? else retry once

-> API adds fixed notice: "Decision support for trained health workers, not a diagnosis."

## 4.3 Repository layout (keep it small)

ilera-atlas/

data/      extract.py  draft_qa.py  translate.py  build_splits.py

bench/     ilera_bench.jsonl (frozen)  eval.py  score.py

train/     train_unsloth.ipynb

serve/     modal_app.py  space/app.py  redflags.yaml

docs/      ARCHITECTURE.md  API.md  SOURCES.md  RESULTS.md

README.md  LICENSE (N-ATLaS terms)  MODEL_CARD.md

## 4.4 Training recipe (starting point)

| Setting | Value |
| --- | --- |
| Base model | NCAIR1/N-ATLaS, loaded in 4-bit (Unsloth FastLanguageModel) |
| LoRA | r = 16, alpha = 16, dropout 0, target q,k,v,o,gate,up,down projections |
| Learning rate / epochs | 2e-4, 2 epochs, cosine schedule, warmup 5% |
| Batch | per-device 2, gradient accumulation 4 (effective 8) |
| Max sequence length | 1,024 (raise to 2,048 only if answers are cut) |
| Chat template | Use the N-ATLaS tokenizer's own chat template; train on the assistant turn only |
| Data mix | About 70% Standing Orders Q&A, 20% case vignettes and referral cases, 10% Aya general data |
| Language mix | About 50% English, 25% Hausa, 25% Yoruba (Igbo if a reviewer is available) |
| Run plan | Run A: English only. Run B: full multilingual mix. Run C: best of A/B with more vignettes. Pick the winner on the validation set, never on the benchmark. |

# 5. Ilera-Bench: how we prove it works

PS3 requires a benchmark of 500+ examples vs base N-ATLaS. We build ours before training and freeze it with a file hash in the repo, so nobody can say we tuned to the test.

| Part | Items | How it is made |
| --- | --- | --- |
| A. Standing Orders, English | 300 | From held-out sections (split by section, not random rows) |
| B. Hausa | 150 | Translated from A-style items, every item fixed by a native speaker |
| C. Yoruba | 150 | Same, with correct tone marks |
| D. External: AfriMed-QA primary-care subset | 300 MCQ | Not written by us, so it shows the gain is real beyond our own data |

| Metric | How it is scored | Automatic? |
| --- | --- | --- |
| Action accuracy | ACTION line matches gold label (Treat / Refer / Urgent) | Yes |
| Key-fact recall | Each item lists 2 to 4 key facts (drug, dose, danger sign); count how many appear | Yes, plus spot check |
| Under-referral rate | Gold says Refer/Urgent but model says Treat. This is the most dangerous error. | Yes |
| Dangerous-advice rate | Clinical reviewer grades 150 answers per model, blind (model names hidden) | No (human) |
| Language fidelity | Answer is in the same language as the question (GlotLID) | Yes |
| Source accuracy | SOURCE line points to the right section | Yes |
| AfriMed-QA MCQ accuracy | Correct option letter | Yes |

Report every metric for base N-ATLaS vs Ilera-ATLAS, per language, with 95% bootstrap confidence intervals. That table is the centre of your submission and your paper.

# 6. Validation with real people

- Blind clinical review: 2 to 3 reviewers (nurse, doctor, or final-year medical/nursing student) grade a random 150 answers from each model without knowing which is which.

- Small user test: 5 to 10 CHEWs or community-health students use the demo page for one session (about 30 minutes each, at least 50 logged questions in total). Collect a 3-question feedback form: was it correct, was it clear, would you use it.

- Consent and privacy: use a one-page consent form, no patient names or real patient data, store logs without personal details. Ask your supervisor whether your department needs an ethics note for a user test; get it early if so.

- External developer test: ask 2 developers outside the team to call the API from the API.md instructions and report time to first answer. This proves "another developer can integrate it".

# 7. Day-by-day execution plan

Today is Thursday 1 October. Eleven working days. Submit on Sunday 11 October if at all possible; keep 12 October as a buffer only.

| Day | Tasks | Done when |
| --- | --- | --- |
| Thu 1 Oct | Form team and roles. Ask HOD for the endorsement letter. Everyone creates Hugging Face, Kaggle (phone-verified), GitHub, Modal accounts and accepts the N-ATLaS gate. Request AfriMed-QA access. | All accounts work; letter requested |
| Fri 2 Oct | Download all Standing Orders PDFs. Extract text with PyMuPDF into one JSON per section. Decide train sections vs held-out benchmark sections. Clinical reviewer drafts the red-flag list. | sections.jsonl exists; split decided |
| Sat 3 Oct | Kaggle: load N-ATLaS in 4-bit, test chat template. Draft Q&A for held-out sections first (benchmark), then training sections. Start the Google Sheet review. | 700+ draft benchmark items |
| Sun 4 Oct | Review and correct benchmark English items. Write key facts and gold ACTION for each. Translate 150 to Hausa and 150 to Yoruba with N-ATLaS; send to native speakers. | English benchmark (300) final |
| Mon 5 Oct | Freeze Ilera-Bench (hash in repo). Run base N-ATLaS on the full benchmark and AfriMed-QA subset. Keep drafting training data. | Baseline numbers saved |
| Tue 6 Oct | Finish training set (target 3,000 to 5,000). Add vignettes, referral cases, Aya 10%. Build train/validation split. Training run A (English) on Kaggle. | Run A finished |
| Wed 7 Oct | Training runs B and C on two team accounts in parallel. Evaluate on validation set. Pick the best run. | Best adapter chosen |
| Thu 8 Oct | Final benchmark run on the chosen model. Export merged + GGUF. Push to Hugging Face (private). Start blind clinical review. | Results table v1 |
| Fri 9 Oct | Deploy Modal API (vLLM) and HF Space (GGUF + Gradio). Add safety layer. Write API.md and test with 2 external developers. | Live URLs work |
| Sat 10 Oct | User test session with CHEWs or students (50+ questions logged). Finish clinical review. Write README, ARCHITECTURE, MODEL_CARD, RESULTS. | All validation evidence in repo |
| Sun 11 Oct | Record the 3 to 5 minute video. Make repos public. Fill the application form. Submit. | Submission confirmation |
| Mon 12 Oct | Buffer only. Fix anything broken; resubmit if the portal allows edits. | - |

After submission: keep the Modal API and HF Space live through the N-ATLaS integration check (15 to 17 October). Watch your Modal credits; scale-to-zero keeps idle cost at zero.

# 8. Team roles (2 to 5 people)

| Role | Owner | Main work |
| --- | --- | --- |
| ML lead (you) | Postgraduate / researcher | Training, evaluation, API, repo |
| Data lead | Student | PDF extraction, draft generation, sheet management, splits |
| Clinical reviewer | Nursing / medical / public-health student | Gold labels, red-flag list, blind review, user test |
| Language reviewers | Hausa and Yoruba native speakers (can be volunteers, credited) | Fix translations of every benchmark item |
| Faculty supervisor | Lecturer | Endorsement letter, ethics advice, paper co-author |

# 9. Risks and fallbacks

| Risk | Fallback |
| --- | --- |
| Unsloth fails to load N-ATLaS | Plain transformers + PEFT + bitsandbytes 4-bit; same recipe, about 2x slower. |
| Kaggle GPU quota runs out | Use another team member's account; then Colab free T4; then Colab Pro. |
| Not enough Yoruba reviewers | Ship English + Hausa fully reviewed; report Yoruba as partial with honest numbers. |
| Fine-tuned model is worse in some area | Report it. Honest negative results are valued in the academic track; explain why in RESULTS.md. |
| Modal credits or setup problems | HF Space CPU API stays live as the official endpoint. |
| HOD letter delayed | Ask on day 1; prepare a one-paragraph draft letter for the HOD to sign. |
| Model gives unsafe advice | Red-flag override, structured ACTION line, under-referral metric, clear notice. Never market it as a diagnosis tool. |

# 10. Licence and compliance checklist

- Release the model under the N-ATLaS Terms of Use (derivatives must use the same licence).

- Name it "Ilera-ATLAS (Powered by Awarri)" and credit "Awarri Technologies and the Federal Ministry of Communications, Innovation and Digital Economy".

- Note the 1,000 active-user cap in your scalability section and describe the commercial-licence path for a national rollout.

- Do not redistribute AfriMed-QA content (CC-BY-SA, gated); publish only the loader and item IDs you used.

- Credit CHPRBN, FMoH, NPHCDA and WHO as the guidance sources in SOURCES.md and the model card.

# 11. What the 3 to 5 minute video shows

- 0:00 to 0:30: the problem (CHEWs, Standing Orders, language gap).

- 0:30 to 1:30: live demo: one English, one Hausa, one Yoruba question; one red-flag case forcing urgent referral.

- 1:30 to 2:30: results table, base N-ATLaS vs Ilera-ATLAS, under-referral rate.

- 2:30 to 3:30: a developer calling the API with curl; Hugging Face model card.

- 3:30 to 4:30: user test evidence, limitations, next steps (more languages, national pilot with CHPRBN).

# 12. Submission checklist (seven items)

| Item | Your evidence |
| --- | --- |
| 1. Working artefact | Hugging Face model + live Modal API + HF Space demo + GitHub repo |
| 2. N-ATLaS integration evidence | adapter_config.json showing base_model NCAIR1/N-ATLaS; training notebook; ARCHITECTURE.md |
| 3. Real-world validation | Ilera-Bench results (600+ items) vs base; blind clinical review; user-test logs; developer test notes |
| 4. Technical documentation | README, ARCHITECTURE.md, API.md, MODEL_CARD.md, SOURCES.md |
| 5. Video | 3 to 5 minutes, end-to-end, uploaded unlisted on YouTube |
| 6. Team profile | Names, institution, roles, short bios |
| 7. Endorsement | Signed HOD letter (PDF) |